## Page3_By Deliverable
REQUEST FOR PROPOSAL (RFP): “Evaluating the Child Guarantee Preparatory Stage, Phase III" ECARO ¦ RFP-ECA-2021-14 ¦ LRPS#9170025 (Page 3)
No | TASKS | DELIVERABLES | TEAM MEMBERS | TOTAL NUMBER OF EXPERTS PROPOSED BY THE VENDOR | DURATION OF THE TASKS PROPOSED BY UNICEF (calendar days) | PROPOSED PERSON-DAYS | PROPOSED UNIT COST (USD) | TOTAL COST (USD)
1 | Getting Started: Kick off meeting | Kick off meeting: presentation and materials | expert 1 (team leader) | 1 | 2 | 1 | 150 | 150
|  |  | expert 2 (evaluator) | 1 |  | 1 | 150 | 150
|  |  | expert 3 (research assistant) | 1 |  | 1 | 150 | 150
|  |  | expert 4 (focal point researcher) | 4 |  | 4 | 100 | 1600
|  |  | expert 5 (designer producer (optional)) | 1 |  | 1 | 75 | 75
|  |  | expert 6 (editor) | 1 |  | 1 | 75 | 75
| TOTAL FOR TASK 1 |  |  | 9 | 2 | 9 |  | 2200
2 | Inception Phase: desk and literature review; first round of interviews ith COs and RO; refining methdological approach; delivery detailed methdological note; deliver draft inception report | Inception report Draft | expert 1 (team leader) |  | 20 |  |  | 0
|  |  | expert 2 (evaluator) |  |  |  |  | 0
|  |  | expert 3 (research assistant) |  |  |  |  | 0
|  |  | expert 4 (focal point researcher) |  |  |  |  | 0
|  |  | expert 5 (designer producer (optional)) |  |  |  |  | 0
|  |  | expert 6 (editor) |  |  |  |  | 0
| TOTAL FOR TASK 2 |  |  | 0 | 20 | 0 |  | 0
3 | Inception phase: received feedback; Revise Inception report, including data collection tools and methodological note; ethical review finalized; integration of feedback | Revised Inception report | expert 1 (team leader) |  | 15 |  |  | 0
|  |  | expert 2 (evaluator) |  |  |  |  | 0
|  |  | expert 3 (research assistant) |  |  |  |  | 0
|  |  | expert 4 (focal point researcher) |  |  |  |  | 0
|  |  | expert 5 (designer producer (optional)) |  |  |  |  | 0
|  |  | expert 6 (editor) |  |  |  |  | 0
| TOTAL FOR TASK 3 |  |  | 0 | 15 | 0 |  | 0
4 | Inception phase: Prepare presentation and Present | Inception Report presentation and materials | expert 1 (team leader) |  | 3 |  |  | 0
|  |  | expert 2 (evaluator) |  |  |  |  | 0
|  |  | expert 3 (research assistant) |  |  |  |  | 0
|  |  | expert 4 (focal point researcher) |  |  |  |  | 0
|  |  | expert 5 (designer producer (optional)) |  |  |  |  | 0
|  |  | expert 6 (editor) |  |  |  |  | 0
| TOTAL FOR TASK 4 |  |  | 0 | 3 | 0 |  | 0
5 | Data Collection and analysis: kII; gathering of operational research data; existing data and evidence; data analysis , triangulation; prepare short interim report with preliminary findings | Short preliminay findings paper | expert 1 (team leader) |  | 40 |  |  | 0
|  |  | expert 2 (evaluator) |  |  |  |  | 0
|  |  | expert 3 (research assistant) |  |  |  |  | 0
|  |  | expert 4 (focal point researcher) |  |  |  |  | 0
|  |  | expert 5 (designer producer (optional)) |  |  |  |  | 0
|  |  | expert 6 (editor) |  |  |  |  | 0
| TOTAL FOR TASK 5 |  |  | 0 | 40 | 0 |  | 0
6 | Data Collection and analysis: Workshop preliminary findings and recommendations co-creation materials | Preliminary findings presentation | expert 1 (team leader) |  | 5 |  |  | 0
|  |  | expert 2 (evaluator) |  |  |  |  | 0
|  |  | expert 3 (research assistant) |  |  |  |  | 0
|  |  | expert 4 (focal point researcher) |  |  |  |  | 0
|  |  | expert 5 (designer producer (optional)) |  |  |  |  | 0
|  |  | expert 6 (editor) |  |  |  |  | 0
| TOTAL FOR TASK 6 |  |  | 0 | 5 | 0 |  | 0
7 | Report Finalization: Final draft evaluation report | Final Evaluation report Draft, including case studies | expert 1 (team leader) |  | 20 |  |  | 0
|  |  | expert 2 (evaluator) |  |  |  |  | 0
|  |  | expert 3 (research assistant) |  |  |  |  | 0
|  |  | expert 4 (focal point researcher) |  |  |  |  | 0
|  |  | expert 5 (designer producer (optional)) |  |  |  |  | 0
|  |  | expert 6 (editor) |  |  |  |  | 0
| TOTAL FOR TASK 7 |  |  | 0 | 20 | 0 |  | 0
8 | Report Finalization: Integration of commens and feedback in the report | Final Evaluation report, including case studies | expert 1 (team leader) |  | 10 |  |  | 0
|  |  | expert 2 (evaluator) |  |  |  |  | 0
|  |  | expert 3 (research assistant) |  |  |  |  | 0
|  |  | expert 4 (focal point researcher) |  |  |  |  | 0
|  |  | expert 5 (designer producer (optional)) |  |  |  |  | 0
|  |  | expert 6 (editor) |  |  |  |  | 0
| TOTAL FOR TASK 8 |  |  | 0 | 10 | 0 |  | 0
9 | Video or Web-based infographic and Evaluation Policy brief (Optional. (Will be considered as a bonus when presenting a proposal)) |  | expert 1 (team leader) |  | 5 |  |  | 0
|  |  | expert 2 (evaluator) |  |  |  |  | 0
|  |  | expert 3 (research assistant) |  |  |  |  | 0
|  |  | expert 4 (focal point researcher) |  |  |  |  | 0
|  |  | expert 5 (designer producer (optional)) |  |  |  |  | 0
|  |  | expert 6 (editor) |  |  |  |  | 0
| TOTAL FOR TASK 9 |  |  | 0 | 5 | 0 |  | 0
10 | Presentation final report and other materials produced |  | expert 1 (team leader) |  | 3 |  |  | 0
|  |  | expert 2 (evaluator) |  |  |  |  | 0
|  |  | expert 3 (research assistant) |  |  |  |  | 0
|  |  | expert 4 (focal point researcher) |  |  |  |  | 0
|  |  | expert 5 (designer producer (optional)) |  |  |  |  | 0
|  |  | expert 6 (editor) |  |  |  |  | 0
| TOTAL FOR TASK 10 |  |  | 0 | 3 | 0 |  | 0
| GENERAL TOTAL |  |  |  | 123 | 9 |  | 2200
(* Entries for task 1 and incidentals table are provided as an example, please delete them and provide your own entries.)
INCIDENTAL EXPENSES (* Entries for task 1 and incidentals table are provided as an example, please delete them and provide your own entries.)
C | C. MISCELLANEOUS EXPENSES (bidders are allowed to give details and may add rows into the excel ensuring that the formulas are not affected throughout the excel template.) |  | Name of the expenditures |  |  |  |  | Total (USD)
| Other expenses (administrative costs, stationery, photocopy, printing, etc.) | [6 empty] | 0
| OVERALL TOTAL for INCIDENTAL EXPENSES (USD) | [6 empty] | 0
* Unit costs should have only two digits after the decimal points.
* Bidders shall submit their price proposals in American Dollars (USD).
* The expected calendar duration for this assignment is 123 days (it does not include days required by UNICEF for review and organization) - Total number of person/days (expert days) can be different than the total duration as per the total number of days each expert will work for this assignment. - Number of experts and the roles of experts who will carry out the assignment should be proposed by the bidders in their technical proposals in detail and this structure should be reflected in this financial proposal together with the number of person/expert days and their daily fees. - The bidders should replicate the rows as per their proposed number of experts and should check all formula on the excel once more to verify the correctness of the formula.
* Only LIGHT YELLOW highlighted columns/cells of the above table should be filled in by the bidders. The other colums are fixed by UNICEF and should not be modified by the bidders. The fixed figures are estimated figures and are subject to change during the course of the programme activities with the prior approval of UNICEF.
* Contracts will be issued by UNICEF in USD. * Payments will be made only after satisfactory completion of the work by contractor and acceptance of the work by UNICEF. * Incidental expenses will be reimbursed to the contractors following completion of the activities and upon receipt of actual expenses with proof&approved documents. * For international contractors, incidental expenses should be reflected in the currency of the country where these have been incurred/paid by the contractor, the reimbursement of incidentals will be made in USD based on the monthly UN exchange rate effective on the date of the service is taken.
NOTES:
1) All fee rates must cover:
- The remuneration actually paid to the experts concerned per working day
- Administrative costs of employing the relevant experts, such as relocation and repatriation expenses, expatriation allowances, leave, medical insurance and other employment benefits accorded to the experts by the Consultant
- The margin covering the Consultant's overheads, profit and backstopping facilities
2) Note that the input of experts must be given in full working days.
3) Note that the last instalment of the price proposal shall not be less than 15 % of the total amount of deliverables.
4)Provisions for incidental expenses: - All incidental expenditures incurred in the course of the contract as required by the Terms of Reference is to be invoiced on the basis of actual cost together with the supporting documents. - Any cost related to the payment of an incidental expenditure is included, such as bank charges. - All incidental expenditure details should be provided separately.

## Page2_By Role
REQUEST FOR PROPOSAL (RFP): “Evaluating the Child Guarantee Preparatory Stage, Phase III" ECARO ¦ RFP-ECA-2021-14 ¦ LRPS#9170025 (Page 2)
No | Proposed Team Member | # of Experts | # of Person/Days | Unit cost per person/day (USD) | Total Cost (USD)
1 | Expert 1 (Team Leader) | 1 |  |  | 0
2 | Expert 2 (evaluator) | 1 |  |  | 0
3 | Expert 3 (research assistant) | 1 |  |  | 0
4 | Expert 4 (focal point researcher) | 4 |  |  | 0
5 | Expert 5 (designer producer (optional)) | 1 |  |  | 0
6 | Expert 6 (editor) | 1 |  |  | 0
xx
| Total cost (USD) |  | 0 |  | 0
- The expected total duration for this assignment is 123 days (it does not include days required by UNICEF for review and organization) - Total number of person/days (expert days) can be different than the total duration as per the total number of days each expert will work for this assignment. - Number of experts and the roles of experts who will carry out the assignment should be proposed by the bidders in their technical proposals in detail and this structure should be reflected in this financial proposal together with the number of person/expert days and their daily fees. - The bidders should replicate the rows as per their proposed number of experts and should check all formula on the excel once more to verify the correctness of the formula.'By Role'!
*Unit costs should have only two digits after the decimal points.

## Page1_Total Cost
REQUEST FOR PROPOSAL (RFP): “Evaluating the Child Guarantee Preparatory Stage, Phase III" ECARO ¦ RFP-ECA-2021-14 ¦ LRPS#9170025 (Page 1)
No | Description | Amount (in USD) | UNICEF's Preferred Payment Schedule
1 | Kick off meeting materials | 2200 | 1st instalment
2 | Inception report Draft | 0 | 2nd instalment
3 | Revised Inception report, including data collection tools and methodological note | 0
4 | Presentation of Inception Report and materials | 0
5 | Short interim report with preliminary findings, including case studies | 0 | 3rd instalment
6 | Workshop preliminary findings and recommendations co-creation materials | 0
7 | Final Evaluation report Draft, including case studies | 0
8 | Final Evaluation Report, including case studies | 0
9 | Video, Web-based Infographic and Evaluation Policy brief (Optional. (Will be considered as a bonus when presenting a proposal)) | 0
10 | Presentation final report and other materials produced | 0
Total for Deliverables |  | 2200
Incidentals
7 | Incidental Expenses as indicated on "By Deliverable" tab | 0
Total for Incidentals |  | 0
TOTAL CONTRACT VALUE (USD) : |  | 2200
*Unit costs should have only two digits after the decimal points.
* Formula on this page is connected with the entries on Page 3. Therefore, please check the entries and the formula at the end.
NOTES:
1) All fee rates must cover:
- The remuneration actually paid to the experts concerned per working day
- Administrative costs of employing the relevant experts, such as relocation and repatriation expenses, expatriation allowances, leave, medical insurance and other employment benefits accorded to the experts by the Consultant
- The margin covering the Consultant's overheads, profit and backstopping facilities
2) Note that the input of experts must be given in full working days
3) Note that the last instalment of the price proposal shall not be less than 15 % of the total amount of deliverables.
4)Provisions for incidental expenses: - All incidental expenditures incurred in the course of the contract as required by the Terms of Reference is to be invoiced on the basis of actual cost together with the supporting documents. - Any cost related to the payment of an incidental expenditure is included, such as bank charges. - All incidental expenditure details should be provided separately.